## Product Backlog
Product Name:
Name:
Initials:
Student ID:
Total Features | Left | Available | Completed | Sprint Ends
Start | 28 | 28 | 0
Sprint 1 | 24 | 28 | 4 | 2018-03-30
Sprint 2 | 22 | 28 | 6 | 2018-04-08
Sprint 3 | 20 | 28 | 8 | 2018-04-15
Sprint 4 | 20 | 28 | 8 | 2018-04-22
Sprint 5 | 20 | 28 | 8 | 2018-04-29
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | As a … | I want to… | So that… | Type | Notes
CM | 1 | C | 1 | 1 | PM | Create any type of media | I can check out media and create bundles | CLI | No Menu Required
BN | 2 | C | 1 | 1 | PM | Create a bundle of media | I can check out bundles | CLI | No Menu Required
| 3 | C | 1 | 1 | PM | Create a Librarian | They can check out/in media | CLI | No Menu Required
| 4 | C | 1 | 1 | LB | Create a Customer | We can keep track of who has what media | CLI | No Menu Required
| 5 | C | 2 | 3 | CU | Browse Catalog | they can see what is available | CLI | Need to list all media. Also list all bundles and media in those bundles. Creating Menu
| 6 | C | 2 | 3 | PM | Add or Create | I can do it from a menu | CLI | Requires MVC
| 7 | NS | 2 |  | LB | Check out Media | Customers can check out books | CLI | Librarian creates transaction with customer info
| 8 | NS | 2 |  | LB | Check in Media | Customers can check in books | CLI | Librarian modifies transaction to check in
| 9 | NS | 2 |  | CU | Pay Balance | Pay fine and check out new books | CLI | Customer can't check out media till balance is paid
| 10 | S | 2 | 3 | PM | Save/Load Data | Don’t loose records of clients, media, and transaction | CLI | Should be options in the menu
| 11 | NS | 3 | 3 | ALL | Open a main GUI Window | I can use my mouse | GUI | Just opening a window
| 12 | NS | 3 |  | PM | Create Media and Bundles Via GUI | Make this process more user friendly | GUI | Be able to do this in dialog windows
| 13 | NS | 3 |  | CU | Browse GUI Catalog | They can see what is available | GUI | Dialog Windows
| 14 | NS | 4 |  | PM | Create Librarians via GUI | They can check out/in media | GUI | Same as before but in a GUI
| 15 | NS | 4 |  | LB | Create Customers via aGUI | We can keep track of who has what media | GUI | Same as before but in a GUI
| 16 | NS | 4 |  | LB | Check out Media in GUI | Customers can check out books | GUI | Same as before but in a GUI
| 17 | NS | 4 |  | LB | Check in Media in GUI | Customers can check in books | GUI | Same as before but in a GUI
| 18 | NS | 4 |  | CU | Pay Balance in GUI | Pay fine and check out new books | GUI | Same as before but in a GUI
| 19 | NS | 4 |  | ALL | See a menu Bar | Make it easier to find stuff | GUI | Still have dialog boxes, but main menu dialog box is replaced with menu bar
| 20 | NS | 5 |  | PM | See everything that’s checked out and to who | See what's not in the library | GUI | A scrollable list
| 21 | NS | 5 |  | PM | Save/Load Data to default file name | Don’t loose records of clients, media, and transaction | GUI | Save to whatever file was opened, or a defualt name
| 22 | NS | 5 |  | PM | Save and Load from different file names | Manage multiple libraries | GUI | Save/load to a user specified file
| 23 | NS | 6 |  | CU | See pictures of the media | So customers can see what book to look for | GUI | Picture must be added when creating media
| 24 | NS | 6 |  | ALL | Have users log in | So not all options are available to everyone | GUI | Can be hardcoded user names and passwords, such as "PM" for project manager with password "password". Each user type must have different usernames and passwords
| 25 | NS | 6 |  | LB | Bulk Check Out/In | So that librarians can check out multiple books at once | GUI | One window where multiple media ids can be typed, and check out multiple customers at once
| 26 | NS | 7 |  | ALL | Undo | Undo mistakes | GUI | Undo events (add media, check out, etc)
| 27 | NS | 7 |  | ALL | Copy Paste | Not waste time typing | GUI | Just do it where you can. It's built in some places. Don't start your own.
| 28 | NS | 7 |  | ALL | Have this in one window | It's not full of pop up dialog boxes | GUI | All contents in a window. Different window layout for different users

## Sprint 1
Sprint # | 1
Start on | 2018-03-24
End on | 2018-03-30
Total Tasks | 8
Day 1 Left | 8
Day 2 Left | 8
Day 3 Left | 5
Day 4 Left | 5
Day 5 Left | 5
Day 6 Left | 3
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CM | Architecture | UML | AD | Add methods to Media and derived classes | C – Completed | Added get methods only.
2 | CM | Media | Code | AD | Write and compile empty Media class | C – Completed
3 | CM | Media | Code | AD | Variables and Constructor | C – Completed
4 | CM | Media | Code | AD | Operator Overload << | C – Completed
5 | CM | Media | Test | AD | Test Constructor and << | C – Completed
6 | CM | Media | Code | AD | Add Get Methods | C – Completed
7 | CM | Media | Test | AD | Test get methods in main | C – Completed
8
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Wrap Up | UML | AD | Update UML to match new methods if changed | C – Completed
N + 1 | BN | Architecture | UML | AD | Add methods to Bundle and derived classes | C – Completed
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Wrap_Up | Delivery | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | C – Completed

## Sprint 2
Sprint # | 2
Start on | 2018-04-02
End on | 2018-04-08
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 3
Sprint # | 3
Start on | 2018-04-09
End on | 2018-04-15
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 4
Sprint # | 4
Start on | 2018-04-16
End on | 2018-04-22
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 5
Sprint # | 5
Start on | 2018-04-23
End on | 2018-04-29
Total Tasks | 0
Day 1 Left | 0
Day 2 Left | 0
Day 3 Left | 0
Day 4 Left | 0
Day 5 Left | 0
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes