## Product Backlog
Product Name: | CSE1325 Video Store Management System
Team ID:
Name:
Initials:
Student ID:
(Additional names for teams only)
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 8
Sprint 1 Left | 8
Sprint 2 Left | 8
Sprint 3 Left | 8
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | As a... | I want to... | So that... | Notes
AM | 1 | NS | 1 | VS | Add Media | I can keep track of what is in the Video Store
LM | 2 | NS | 1 | VS | List all media | I can find out what is in the Video Store | This will also be needed for the next two features
CO | 3 | NS | 1 | VS | Check out Media | I can track who has borrowed each media | Each media will need to know if it is checked out or not
CI | 4 | NS | 1 | VS | Check in Media | I can tell when a media is returned
HE | 5 | NS | 1 | VS | Get help | I can learn how to use the system
PA | 6 | NS |  | VS | Add a patron | I can conveniently keep track of all patrons | This is the Bonus level
SP | 7 | NS |  | VS | Select a patron when checking out a Media | I don't have to rekey recurring patron info | This is the Bonus level
CU | 8 | NS |  | VS | Add custom info for each media type | I can keep better track of video store assets | This is the Bonus 2 level

## Sprint 01 Backlog
Sprint # | 1 |  |  |  | ***SPRINT 1***
Start on | 2017-09-23
End on | 2017-09-30
Demo on | TBD
Total Tasks | 15
Day 1 Left | 10
Day 2 Left | 8
Day 3 Left | 7
Day 4 Left | 4
Day 5 Left | 4
Day 6 Left | 2
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
CON | AM |  | code |  | make enums file for genre, age and media type | Done
| AM |  | test |  | Create a Media class with data and a constructor | Done
TS | AM |  | code |  | Write a test for the Media class | Done
| AM |  | test |  | Add the to_string method to Media | Done
ICO | AM |  | code |  | Add tests for the to_string method | Done
| AM |  | test |  | Make video store class for the media library | Done
CO | AM |  | code |  | Test video class | Done
| AM |  | test |  | Add the check_out method to Media | Done
CI | AM |  | code |  | Add tests for the check_out method | Done
| AM |  | test |  | Add the check_in method to Media | Done
| LM |  | test |  | Add tests for the check_in method | Done
| CO |  | code |  | start making main | Done
| CI |  | code |  | use makefile to test main | Done
| HE |  | code |  | make test all file?? | Done
| PA |  | test |  | run final program | Done
| SP |  | test |  | debug | Done