## Product_Backlog
Product Name:		Robbie Robot Shop					Fields in blue expect your input!
Team ID:		Kings

Name:		Tausif Zaman
Initials:		T.Z.
Student ID:		1001415041

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	11	32
Sprint 1	10	32	1	Oct 29
Sprint 2	8	32	2	Nov 05
Sprint 3	4	32	6	Nov 12
Sprint 4	4	32	6	Nov 19
Sprint 5	4	32	0	Nov 26
Sprint 6	4	32	0	Dec 03

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1		Pts	Cml	As a...	I want to...	So that...	Type	Notes
	1	CO	1	1		21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
	2	CO	2	2		13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
	3	CO	2	2		5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
	4	CO	3	3		3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
	5	CO	3	3		3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
	6	CO	3	3		8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
	7	CO	3	3		13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
	8	NS	4	4		3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
	9	NS	4	4		34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
	10	NS	5	5		21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
	11	NS	6	6		8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS				21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS				13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
	14	NS				8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
	15	NS				5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS				13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS				5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS				8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS				8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS				8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS				8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS				8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS				13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS				21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS				13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS				8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS				8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS				21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_1
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	10/22/17 12:00 AM
End on	10/29/17 12:00 AM
Demo on

Total Tasks	25
Day 1 Left	25
Day 2 Left	22
Day 3 Left	17
Day 4 Left	11
Day 5 Left	8
Day 6 Left	4
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assgnd To	Description	Status	Notes
1	Create_Parts	Architecture	UML	TZ	Create and document use case diagram	NS - Not Started
2	Create_Parts	Architecture	UML	TZ	Add view and controller section to class diagram	NS - Not Started
3	Create_Parts	Architecture	UML	TZ	Add methods to Robot_part and its derived classes	NS - Not Started
4	Create_Parts	Robot_part	Code	TZ	Write and compile empty class Robot_part	NS - Not Started
5	Create_Parts	Robot_part	Code	TZ	Add data fields and constructor to Robot_part and compile	NS - Not Started
6	Create_Parts	Robot_part	Code	TZ	Overload operator<< and compile	NS - Not Started
7	Create_Parts	Robot_part	Test	TZ	Create main() regression test for Robot_part and test it	NS - Not Started
8	Create_Parts	Robot_part	Code	TZ	Add getters to Robot_part and compile	NS - Not Started
9	Create_Parts	Robot_part	Test	TZ	Update regression test to verify getters	NS - Not Started
10	Create_Parts	Head	Code	TZ	Create Head class derived from Robot_part and compile	NS - Not Started
11	Create_Parts	Head	Test	TZ	Adapt regression test to verify getters	NS - Not Started
12	Create_Parts	Head	Code	TZ	Add power field and compile	NS - Not Started
13	Create_Parts	Head	Test	TZ	Add test for power field	NS - Not Started
14	Create_Parts	Arm	Code	TZ	Create Arm class derived from Robot_part and compile	NS - Not Started
15	Create_Parts	Arm	Test	TZ	Adapt regression test to also test Arm	NS - Not Started
16	Create_Parts	Locomotor	Code	TZ	Create Locomotor class derived from Robot_part and compile	NS - Not Started
17	Create_Parts	Locomotor	Test	TZ	Adapt regression test to also test Locomotor	NS - Not Started
18	Create_Parts	Torso	Code	TZ	Create Torso class derived from Robot_part and compile	NS - Not Started
19	Create_Parts	Torso	Code	TZ	Add battery_compartments and max_arms	NS - Not Started
20	Create_Parts	Torso	Test	TZ	Adapt regression test to also test Torso	NS - Not Started
21	Create_Parts	Battery	Code	TZ	Create Battery class derived from Robot_part and compile	NS - Not Started
22	Create_Parts	Battery	Code	TZ	Add power_available and max_energy	NS - Not Started
23	Create_Parts	Battery	Test	TZ	Adapt regression test to also test Battery	NS - Not Started
24	Create_Parts	Wrap_up	UML	TZ	Update the UML to conform to any changes during sprint #1	NS - Not Started
25	Create_Parts	Wrap_up	Delivery	TZ	Zip and deliver sprint #1 UML	NS - Not Started
Sprint Burn Chart
Days
Tasks

## Sprint_2
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	22
Day 1 Left	18
Day 2 Left	16
Day 3 Left	15
Day 4 Left	11
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	define new robot models	orders	Code	TZ	take orders	CO
2	define new robot models	models struct	Code	TZ	choose from the models	CO
3	define new robot models	arm size	Code	TZ	choose arms	CO
4	define new robot models	battery size	Code	TZ	choose batteries	CO
5	define new robot models	parts cost	Code	TZ	cost of indiviual parts	CO
6	define new robot models	total cost	Code	TZ	total cost of a robot model	CO
7	browse a catalog of robot models	display models	Code	TZ	display models available	CO
8	browse a catalog of robot models	buy models	Code	TZ	buy a model	CO
9	browse a catalog of robot models	price of a model	Code	TZ	show price of robot model	CO
10	create a new Beloved Customer	set customer name	Code	TZ	Set Customer name	CO
11	create a new Beloved Customer	get customer name	Code	TZ	Show customer name	CO
12	create a new Beloved Customer	customer list	Code	TZ	Show list of customers	CO
13	create a new Sales Associate	set associate name	Code	TZ	Set associate name	CO
14	create a new Sales Associate	get associate name	Code	TZ	show associate name	CO
15	create a new Sales Associate	associate list	Code	TZ	show list of associates	CO
16	create a robot order for a Customer	create order	Code	TZ	create new order	CO
17	create a robot order for a Customer	view order	Code	TZ	view order details	CO
18	create a robot order for a Customer	show total price	Code	TZ	show total price of order	CO
19	ensure persistence of the RRS data	save data	Code	TZ	save data, newly created parts	CO
20	ensure persistence of the RRS data	load data	Code	TZ	show newly created parts	CO
21	load again after running the program	load data	Code	TZ	show new parts after reopening program	CO
22	Update class diagram	Update	UML	TZ	Add the new things added to the program	CO
Sprint Burn Chart
Days
Tasks

## Sprint_3
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks

## Sprint_4
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks

## Sprint5
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks

## Sprint_6
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks